LIST OF WORK, 7th CIRCLE, CHAMBA (EDUCATION)

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Status of Work Supplied by SE. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 7732 | Govt. High School Rei (Pangi) | 25/11/2013 | 18/12/2013 | 02/08/2014 | 27/01/2014 | Tender under process. | --- |
| 2 | 6171 | Girls Hostel in DIET at Saru, Chamba | Standard drawing for 100 girls students | 23/04/2015 | --------- | --------- | First floor columns completed | . |
| 3 | 7732 | Sr. Sec. School at Khanni, Bharmour C/o science block | --------- | 19/05/2009 | --------- | 02/02/2010 | Foundation work is in progress. |  |
| 4 | 7732 | C/O govt. High School Building at Leswin Tehsil Churah distt Chamba. Additional accommodation) |  | Letter no. 5327 dt. 24/08/16 | Letter No. EDN-H(9)2-5/14-Vol-III (BLDG) Chamba June 2017 | Letter No. 17274 dated 04/01/2017 | Tender under process . | ---- . |
| 6 | 7811 | Degree College at Chamba (PG Block) | Letter no. 604-606 dt 11/9/2016 Letter no. 22143 dt 27/03/2017 | Letter no.10270-72 dt 15/09/2016 |  | E.E Chamba letter No. 8121 dated 11/08/2017 | Working drawings received. |  |
| 7 |  | Govt. Degree College, Salooni |  | Fresh contour site plan 29/12/2012 X-section of Admin block | 28/05/2013 | 30/05/2013 | Admin block building work completed month ending 8/2017and handed over to concerned department on 5/9/2017 and Art Block roofing and finishing work is in progress. | --- |
| 8 | 7910 | Govt. Degree College Killar | 27/08/2008 | 03/09/2008 & 08/01/2013 | 06/11/2008 | 06/11/2008 | Roofing work is completed and finishing work is in progress. | ---- |
| 9 | 7845 | Govt. Degree College Bharmour | Requirement received on 21/2/2005 from Director. | Site plan received on 16/11/2005 & revised site plan received on 03/03/3006, 04/09/2009 & revised new Site plan 26/02/2010 | 23/10/2010 | 03/11/2010 | Tender case under process in the O/o Chief Engineer Dharamsala for Negotiation. |  |
| 10 |  | I.T.I Pangi Distt. Chamba | 16/08/2008 revised site plan | 29/8/2008 | 06/11/2008 |  | Finishing work of Block B is in progress . |  |
| 11 | 8170 - | I.T.I Lachori Distt. Chamba | Letter No. 13861 dated 09/03/2017 | Letter No. 17272-75 dated 20/01/17 | Letter No. 47132 dated 04/07/2017 | E.E Chamba No.8842-43 dated 01/08/2017 | Revised W/D issued.(change of canteen into store) Letter No.1629-31 dt.27/07/17 | ---- |

| OFFICE OF THE SENIOR ARCHITECT (KANGRA ZONE) HP PWD DHARAMSHALA |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WORKS OF EDUCATION DEPARTMENT (ONGOING PROJECTS) |  |  |  |  |  |  |  |  |  |
| 7 th CIRCLE - DALHOUSIE |  |  |  |  |  |  |  |  |  |
| Sr. No | Job No. | Name of Project | Date of receiving site Plan | Date of requirments | Date of issue of Drawings | Date of feasibility | Date of approval | Status of Work Supplied by SE. | Remarks |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| SCHOOLS |  |  |  |  |  |  |  |  |  |
| 12 | 105 | Addtitional accommodation GSSS at Kihar. | 16/10/2014 | 16/10/2014 | 24/1/2015 std. working Drawing | 28.02.2015 | 19.02.2015 | The excavation in foundation of 10 columns completed. Lean concrete laid and bottom ,footing cased | --- |
| 13 | 310 | Strenghening of infrastructure of existing school under RMSA of GSSS at Dihur. | 13/8/2014 | 13/8/2014 | 9/12/2014 Sketch drawing 27/3/2015 working drawing | 4/3/2015 | Std. drawings | G.F.& Ist floor slab laid & internal plastering of G.F & F.F. completed. | --- |
| COLLEGES |  |  |  |  |  |  |  |  |  |
| 14 | 347 | Govt Degree College at Sihunta | 04.01.2017 | 02.01.2017 | 27.03.2017 sketch drawings 17.05.2017 working drawings | 17.04.2017 | 17.04.2017 |  | Arch. Drawing received from Sr.Arch.KZ Dharamshla vide letter No. PW-KZ-304/2016-17- 616-20 dt. 27.12.2017 . Working estimate approved by CE (KZ) D/Sla letter No. PW/CE/KZ/CTR-I 2016-17-1124-25 dt. 16.8.2017. Revised estimate send to Dr.Higher Education vide CE (KZ) D/Sala letter No. 4225-28 dt. 26.12.2017 |
| TECHNICAL EDUCATION |  |  |  |  |  |  |  |  |  |
| 15 | 354 | ITI at Dadima, Teh-Bharmour | 12.12.2016 | 28.11.2016 | 22.06.2017 sketch drawings | - | - | Alternative site awaited | Site not handed over by concerned deptt.. |

Note :- Red portion shows  deposit works Which are not counted in Total Projects