LIST OF WORK, 7th CIRCLE, CHAMBA (MISC)

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Status of Work Supplied by SE. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 8107 | Mini Sectt. building at Chamba | April, 2015 | 13/01/2015 | ------------- | ------- | . Sketch drawing alongwith No 1 to 7 supplied on 29-07-2015 | Expenditure Sanction awaited. |
| 2 | 8107 | C/O Rajasav Sadan Building in Revenue Colony at Hardaspura Distt Chamba | Letter No. 2122 dated 05/06/2017 supplied by E.E Chamba. |  |  | From E.E Chamba letter no. 3950 dated 26/07/2017 | Sketch drawings and layout plan has been issued Letter No. 1821-24 dated 04/08/2017 | Working Drawings received. |
| 3 | 8010 | Samiti Bhawan, Killar | 02/08/2010 (from BDO Pangi through E.E.) | 05/03/2011 |  |  | Letter sent to E.E. Killar Division on 18/07/2012 for site detail (no information received till today) | Work executed by B.D.O. Pangi |
| 4 | 7978 | Mini Sectt. Killar | Revised requirement received on 23/06/2015 from R.C. Pangi at Killar | 25/09/2013 revised site plan | 18/06/2014 (Approval on revised drawings ) | 07/06/2014 | Tender under process. |  |
| 5 | 8043 | Existing Bus Stand at Killar | 16/12/2013,alongwith contour site plan through E.E. killar. on dated: 25/11/2013 | 25/11/2013and revised site plan on 17/12/2013 |  |  | Site development work is in progress. | Project is under CM Priority |
| 7 | 3969 | C/O Chaurasi Temple at Bharmour distt. Chamab (Main entrance gate) |  | Letter No. 18003 dated 06/02/2017 |  |  | Layout plan & working drawings issued Letter No 399-402 dated 06/05/17 | feasibility report awaited from A.E. Office Bharmour. |
| 8 | 8195 | C/O Indoor Auditorium at Chamba HP. | Letter No. 4542 dated 02/05/17 Letter No. 6147 dt. 30/06/2017 |  |  |  | Letter issued to E.E Chamba for contour site plan & site details Letter No. 1295-97 dt. 06/07/2017 | Working Drawings awaited. . |
| 9 | 7954 | C/O Ambedker Bhawan at Tissa Distt. Chamba HP | Letter No. 515 dated 25/04/17 ( Contour site plan and requirements has been received) |  |  | From E.E Chamba Letter No. 9894 dated 04/09/2017 | Site not handed over by concerned department. |  |
| 10 | 6465 | C/O PWD Rest house at Bairagarh in Tehsil Churah distt. Chamba |  | E.E Chamba Division letter No. 12764 dted 10/10/2017 |  |  | Letter issued to E.E regarding detailed site plan.Letter No. 2857-59 -dated 23/10/2017 |  |
| 11 | 7531 | C/O Rest House at Bhelai Chamab |  | 9189-90 dated 23/9/2016 |  | Letter No. 13596-97 dated 9/12/2016 | Site development work is in progress |  |
| 12 | 7494 | C/O SDAMD Office cum residence at Killar chamba | Letter No. 12811-13 dated 26/7/13 Received from EE and framed by Resident commissioner Killar at Pangi | Letter No. Letter No. 12811-13 dated 26/7/13 | Letter No. 892 dated 15/7/2014 | Letter No. 31522 dated 27/1/2014 | Tender under process. |  |

List of works 7th Circle (Police)

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Status of Work Supplied by SE. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 13 | 3390 | Police station at Bharmour (Police station cum residential complex ) | 08/01/2014 from SHO | Letter No. 4565 dated 19/06/2017 | Letter No 22721 dated 25/07/2017 Vide letter 2307 dt. 23/01/2017 | Letter No. 7276-78 dated 02/07/14 | Revised W/ Drawings issued on dated 28/10/2017 | feasibility report awaited from A.E. Office Bharmour |
| 14 | 3993 | Police Station at Chamba |  |  |  |  | Approval received from DGP on dated 29-10-15 vide letter No. 32571 drg.No. 23,24 | . |
| 15 | 3993 | Police Check Post at Nakrot Tehsil Churah Distt. Chamba. |  |  | Approval received from director vide letter No 32571 dated 29-10-15 | Feasibility still awaited. | Site not handed over by concerned department. |  |
| 16 | 3993 | C/O Office building and staff quarters CID Wing police line Chamba | Letter No. 20561 dated 24/06/2017 received from Director General of Police State CID Shimla-9 | Letter No. 2836 dated 16/05/2017 received from E.E Chamba Division. | From Addl. General of Police State CID HP. Shimla letter No. 28315 dated 28/08/2017 | From E.E Chamba letter No. 10624 dated 14/9/17 | Tender Invited. . |  |
| 17 | 3390 | Police Station at Killar distt. Chamba HP. |  | 4468-70 dated 25/07/2016 & Photographs of the site received. | Vide letter no 2307 dt. 23/01/2018 |  | DPR under process. |  |

| BUILDING WORKS OF POLICE DEPARTMENT (ONGOING PROJECTS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7 th CIRCLE - DALHOUSIE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sr. No | Job No. | Name of Project | Date of receiving site Plan |  | Date of requirments |  | Date of issue of Drawings |  | Date of feasibility |  | Date of approval |  | Status of Work Supplied by SE. |  | Remarks |
| 1 | 2 | 3 | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |
| 18 | 226 | Office building for Comdt Home Gds 8th Bn Chamba | 18.01.2017 |  | 11.01.2017 |  | 27.02.2017 sketch drawings |  | Awaited |  | 21.03.2017 |  |  |  | Feasibility recenly submitted. |
| 19 | 332 | Police Chowki at Banikhet | 14-12-2015 |  | 10/12/2015 |  | 10.06.2016 Layout plan and working drawing |  | 02.06.2016 |  | Std. drawings |  |  |  | Project assigned to HIMUDA |
| 20 | 298 | Fire Station building at Banikhet | 03.01.2017 |  | 03.01.2017 |  | 15.06.2017 working drawing |  | 20.05.2017 |  | Std. drawings |  |  |  | Feasibility drawing received from Sr.Arch. Dharamshla vide letter No. PW/Ar./KZ/298-2017-18-1515-156 dt. 15.6.2017 and feasibility report submitted to Sr.Architect Dharamshala vide EE Dalhousie letter No. 2460-61 dt. 20.5.2017. Preliminary estimate send to Commnd.Home Guard ,Chamba vide this office letter No. 4318-20 dt. 1.7.2017 |
| BUILDING WORKS OF GAD DEPARTMENT (ONGOING PROJECTS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 th CIRCLE - DALHOUSIE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sr. No | Job No. | Name of Project |  | Date of receiving site |  | Date of requirment |  | Date of issue |  | Date of feasibility |  | Date of approval |  | Status of Work Supplied by SE. | Remarks |
| 1 | 2 | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 | 10 |
| 21 | 218 | Additional and alternation of PWD Rest House at Sach ( Killar) |  | 23/1/2007 |  | 23/1/2007 |  | 16/7/2007 working drawing |  |  |  |  |  | Roofing work completed and finishing work is in progress | --- |
| 22 | 287 | Addtiton /Alternation of Inspection Banglow at Sural Pangi. |  | 9/8/20111 |  | 9/8/2011 |  | 10/9/2012 Sketch Drawing. |  | Awaited |  | Awaited |  |  | Work not pertain to this Deptt. |
| BUILDING WORKS OF MISC. DEPARTMENT (ONGOING PROJECTS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 th CIRCLE - DALHOUSIE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sr. No | Job No. | Name of Project |  | Date of receiving site |  | Date of requirment |  | Date of issue |  | Date of feasibility |  | Date of approval |  | Status of Work Supplied by SE. | Remarks |
| 1 | 2 | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 | 10 |
| 23 | 259 | Sports Stadium at Ajog in Teh. Pangi. |  | 19.12.2009 |  | 19.12.2009 |  | 3/3/2010 Layout Plan 2/2/2011 Working Drawing |  | 10.03.2010 |  | 10.03.2010 |  |  | Scheme not functioned due to non availability of sufficient land |
| 24 | 271 | Tourist Facilitation at Kharamukh ( Chamba Kharamukh road) |  | 28.09.2010 |  | 28.09.2010 |  | 12/1/2011 sketch drawing |  | Awaited |  | 31.01.2011 |  |  | Site not handed over by concerned deptt.. |
| 25 | 283 | Taxi Stand at Killar. |  | 3/4/2012 |  | 3/4/2012 |  | 19/5/2012 Sketch Drawing 10/12/2012 working Drawing 03/8/2015 revised working drawing |  | 1/8/2012 |  | 1/8/2012 |  | Slab laid on ground floor | --- |
| 26 | 246 | Residance cum Office for Assitant ADA at Dalhousie. |  | 14.02.2011 |  | 14.02.2011 |  | 23.07.2011working Drawing |  | Awaited |  | Std. drawings |  |  | Work not pertain to this Deptt. |
| 27 | 294 | Toll Plaza at Katori Bangla. |  | 18/5/2013 |  | 18/5/2013 |  | 5/6/2013 Sketch Drawing 11/10/2013 Working drawing |  | 24.06.2013 |  | 08.10.2013 |  |  | Woring estimate received from Sr.Arch.Dharamshla vide letter No. PW-Arch/KZ/294-2013-14-325-28 dt. 11.10.2013. Detailed estimate send to the Assistant Excise And Taxation Commissioner.Chamba vide EE Dalhousie letter No. 372-74 dt. 26.12.2013 . |
| 28 | 319 | Bus stand at Killar |  | 8/6/2015 |  | 6/6/2015 |  | 30/6/2015 sketch drawings 22-09-2015 working drawings |  | 21/7/2015 |  | 3/8/2015 |  | Site development work is in progress. |  |
| 29 | 330 | Sports Stadiuam at Sadar Bazar Dalhousie |  | 9/11/2015 |  | 5/11/2015 |  | 07-04-2016 Sketch Drawing |  | 12.04.2016 |  | Awaited |  | Pushta work is in progress. | Working drawing received from Sr.Arch Dharamshala vide letter No. PW/Arch.KZ/330/16-17-04-03 dt. 4.7.2016. Work is in progess. |
| 30 | 334 | Stadium at Chowari, Distt Chamba |  | 25.6.2016 |  | 25.6.2016 |  | 15.11.2016 sketch drawings |  | 03.01.2017 |  | Awaited |  | Retaining wall work is in progress. | Working drawing received from Sr.Arch Dharamshala vide letter No. PW/Arch.KZ/ 344/16-17-367-71 dt. 15.11.16. Partly work for site development work is in progress. |
| 31 | 333 | Community Centre cum commericial complex at Bharmour, Chamba |  | 28/03/2016 |  | 19/03/2016 |  | 13/5/2016 sketch drawing 18.07.2016 revised sketch drawing |  | 23.06.2016 |  | Awaited |  |  | Project assigned to HIMUDA |
| 32 | 350 | Ram Leela Ground /Stadium at Killar, The-Pangi |  | 17.12.2016 |  | 09.12.2016 |  | 25.03.17 sketch drawing 21.04.2017 working drawings |  | 31.03.2017 |  | 29.3.2017 |  |  | Structural drawing of plinth,cloumn ,beam and roofing work is still awaitd from the Sr.Architect office Dharamshala. |
| 33 | 361 | Stadium at Motla Distt. Chamba |  | 18.07.2016 |  | 13.07.2016 |  | 07.12.2017 sketch drawing |  | Awaited |  | Awaited |  |  | Feasibility drawings received from Sr.Arch.Dharamshala vide letter No. PW-Arch./KZ/361/2017-18-470-77 dt. 12.12.2017 |

Note :- Red portion shows  deposit works Which are not counted in Total Projects