| List of Work College (Education )Nahan Circle |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No | Job No. | Name of Project | Date of requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Remarks. |
| Colleges In 12 Circle Nahan |  |  |  |  |  |  |  |  |
| 1 | 8137 | C/O Govt College (Anj Bhoj)At Bharli Distt Sirmour | EDN-H (9)1-Policy /2009 dated 31/10/2015 | 4613-14 Dated14/12/2015 | Dated 30/1/2016 | 5152-53 dated25/2/2016 14745-48 dated 4/2/2016 | Working drawing issued vide letter no 4606-09 dated 19-1-2016 Layout plan working drawing with specification issued vide letter no 97-99 dated 6-4-2016 | 40% work completed. (Block B Frame structure completed and Roofing & finishing works of block B is in progress and Block C columns raised upto first floor slab level). |
| 2 | 7035 | C/o Govt Degree College Paonta Shahib (New Academic Block) | EDN-HE(9) 4-1/2007 GC (Paonta Sahib) dated 12/11/2014 | 5998-6000 dated 26/12/2014 | EDN-H(9)4-1/2007 (build) paonta sahib dated 4/9/2015 | 1579 dated 3/6/2016 | Sketch drawing along with layout plan issued vide letter no 2417-21 dated 28/8/2015 | 10 % work completed. RCC foundation and 16 nos column laid. |
| 3 | 7848 | C/O Govt Degree College Sangrah Distt Sirmour | Dated 11-5-2010 Dated 21-7-2015 EDN-HE (9) 4-51/2011 dated 21/10/2016 (Residential Accommodation ) | 1410-15 Dated 28-5-2015 10893-96 dated 16/11/2017 | EDN-H (9)4-5/2007 Dated 13-9-2010 |  | Revised layout plan at Sangrah of residential accommodation issued vide letter no 2069-73 dated 18/8/2010 | Tender for one No Type V Qtr awarded to the contracto & site development work is in progress. where as the Hostel Type Accommodation requirement has been Submitted to the director of higher Education /Architect Shimla fpr Praparetion of Drawings /requirement vide this office Letter No 10893-96 dated 16.11.2017 |
| 4 | 8153 | C/O Govt Degree College Kaffota Tehsil Paonta Sahib Distt Sirmour | EDN-H(9) 1-Polcy /2009 dated 20/10/2015 | 515-17 dated 19/4/2016 | EDN –HE (9)4/18/ 2007 Dated 18/5/2016 | 7718-19 dated 27/12/2016 | Working drawing issued vide letter no 624-27 dated 17-5-2016 | Tender for one No Type V Qtr awarded to the contracto & site development work is in progress. where as the Hostel Type Accommodation requirement has been Submitted to the director of higher Education /Architect Shimla fpr Praparetion of Drawings /requirement vide this office Letter No 10893-96 dated 16.11.2017 |
| 5 | 7842 | C/O Govt Degree College Shillai | dated 13/9/2010 | 4862-64dated 14-10-2005 2263-64 dated 17/6/2009 |  | 128-29 dated 7-4-2016 | Working drawing issued with specification vide letter no 128-29 dated 7/4/2016 | College building ,Type-V qtr & Canteen block Completed Type-IV Ground floor slab laid, Type- I & III 85% work complete finishing work is in progress |

| List of Work Education(School) 12th Circle Nahan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | 6546 | C/O Govt High School Mattar Distt Sirmour | Dated 29-12-2015 |  |  |  |  | Contur site plan is being prepared which will be sent to Chief Archtect Shimla very shortly for evolving the working drawing. |
| 9 | 6546 | C/O Govt High School Maina Distt Sirmour | EDN-H (9)4-14 /2012Dated 18/1/2016 |  |  |  | Letter issued for requirement vide letter no 2442-46 dated 1/9/2015 | GAD is awaited |
| 10 | 6546 | C/O Govt Sr Sec School Gahanduri Distt Sirmour | EDN-H (9)4-14/2012 dated 23/6/2014 | 10177-82 dated 31/10/2013 | EDN-H (9)4-14 dated 15/1/2015 |  |  | 75% work for two rooms and examination hall completed. Revised site/Contour plan is to be Submitted for Revised feasibility for balance Accommodation. |
| 11 | 6546 | C/ O Govt High School Madwach | EDN-H (9) 4/14/2012 Dated 8/5/2017 | 5355-58 dated 6/9/2016 |  |  |  | Letter issued for requirement vide Chief Architect letter 2109-12 dated 21.09.2016 |
| 12 | 6546 | C/o Govt sr sec school Nohradhar Distt Sirmour |  | 29-31 dated 7/4/2017 | EDN-H (9) 4-14/2012 dated 25/5/2017 |  | Layout plan, working drawing along with specification issued for approval vide letter no 464-67 dated 12/5//2017 | Estimate Prapared and is being submitted Sortly for Approval. |
| 13 | 6546 | C/o Govt Sr sec school at Sangrah distt Sirmour HP (Additional 8 Room Govt. Sr. sec. School Sangrah ) | No EDN-B-Ga (1)-5/2014 dated 2014&EDN-HE (9)1-2/2016 -17 dated 8/2016 | 8643-44 Dated 21/8/2017 10711-13 dated 26/10/17 |  |  |  | Site development work is in progress & GAS awaited. |