List of Work Education (School) 4th Circle Shimla

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 1 | 6625 | Contour Site plan for the C/o Govt. High School Sari | No. E.D.N. – H (9) 3- D.H.E., dated: 04/12/2009 |  |  |  |  |  | On going work |
| 2 | 6625 | Govt. Sr. Sec. School at Gaumma, Kusumpti | NO. E.D.N.-H (9)3-19/2008, D.H.E., dated: 14/05/2010 |  |  |  |  |  | _ |
| 3 | 6625 | Govt. Sr. Sec. School at Piran | No. E.D.N.-H(9)3-, D.H.E. dated: 31/12/2008 |  |  |  |  | Old building yet to be demolished. | _ |
| 4 | 6625 | Govt. Sr. Sec. School Junga distt Shimla |  |  |  | EDN –H(9) 3-18/2008 dated 20/2/2016 | 35603-5 dated 23-3-2016 | 50% work completed. | On going work |

RURAL DHAMI, DIVISION, EDUCATION (TEHSIL-SUNNI)

| Sr. NO. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 5 | 6432 | C/o Science block at Govt. Sr. Sec. School at Banuna, Suni |  | No. Jalog/2015-16-1106-07, dated: 17/04/2015 E.E.Shimla Rural Division Letter No 22920-21. Dated 6/10/2015 |  | EDN-H (9) 3-18/2008 dated 19/6/2015 | 36829-30 dated 17/3/2016 |  | Tender called. |
| 6 | 6432 | C/o Mini Stadium at Thachi at Sunni /Sr. Sec. School Thachi Tehsil Suni |  | No. Thachi 2015-16-274-75, dated: 06/04/2015 Site plan received from E.E.Dhami Vide letter no 36405-06 dated 10/3/2016 |  |  | 9126-27 Dated 14/7/2017 | Layout Plan & Working drawing issued vide this office letter no 89-91 dated 6/4/2016 | Work executive by Block. |
| 7 | 6432 | C/o building Govt. Sr. Sec. School Thaila | No. E.D.N.-H (9)3-19/ 2008, D.H.E.date: Nov., 2014 No Shiksha Chalal Thachi-444-46 Dated 7/11/2015 |  |  | 3104-05 dated 13-5-2016 |  |  | Tender under process. |
| 8 | 6432 | C/o Sr. Sec. School building at Neen |  | No./ 2014-15, 7900-01, dated: 2/08/2014 & No. 3189-90, dated: 02/06/2014 &7739-40 dated 20/7/2016 |  | EDN –H (9) 3-18/2008 dated 27/9/2016 | 3104-05 dated 13/5/2016 | Working drawing along with specification issued vide letter no 2069-72 dated 19/9/2016 | 30% work completed. |
| 9 | 6432 | C/o Govt. Sr. Sec. School, Dharogra |  |  | No./ 15-6556-57, dated: 18/07/2014& No./ 2014/- 4461-64, dated: 01/03/2014 & No./ 2014-635-37, dated: 19/05/2014 | No. E.D.N.-H(9)3-18/2008, D.H.E., dated: 29/11/2013 | No. 5321-22, dated: 01/07/2014 | Work drawing issued vide letter no 3582- 84 dated 3/12/2014 | Tender being awarded. |
| 10 | 6432 | C/o Govt. Sr. Sec. School Thaila, Distt. Shimla | No EDN –H (9) 3-19/2008 dated /22/10/2014 | 7735-36 dated 20/7/2016 |  |  |  | Letter issued for requirement vide letter no 1573-76 dated 30/7/2016 Layout plan ,working drawing alongwith specification Issued vide letter no 3924-28 dated 30/1/2017 | Tender under process, |
| 11 | 6432 | C/O Govt Middle School Jamog the Suni Distt Shimla | Requirement received from E.E. Rural Division Dhami .Vide no 34771-73 dt.16-2-2016 | Revinue Paper received from E.E. Rural Division Dhami. Vide letter no 34771-73 dated 16/2/2016 |  |  | 10003-04 dated 20/8/2016 | Working drawing & specification issued vide letter no 5203-05 dated 3/2016 | Build., construction work executed by SMC of School. |
| 12 | 6432 | C/O Govt High School Building at Garkhan Tehsil Suni | No EDN-H (9) 3-19/2008 dated 15/2/2016 | 1221-22 dated 22-3-2016 |  |  |  |  | Build., construction work executed by SMC of School |
| 13 | 6432 | C/o Govt. High School building at Chanawag | Requirement received from Principal Dated 11/8/2015 No EDN-H(9)3-19/2008dt. 26/9/2015 11163-65 dt 3/9/2016 | Letter no 14356-57 dated 11/8/2015 Site Plan received From E.E. |  |  | No./ 2013-14, 6934-35, dated: 17/02/2014 | Revised layout plan ,working drawing alongwith specification issued vide letter no 3491-94 dated 23/12/2016 | Tender is being called. |
| 14 | 8159 | C/o BEEO (Block Elementary Education Office) office building at Sunni, Tehsil Sunni Distt Shimla | -9-27/2001-05 Dated 1/7/2017 No EDN-H (ELe) (4)-9-27/2001-05 dated 9/8/2017 | 4222-23 dated 1/6/2016 |  | EDN-H (Ele)(4)-9-27/2001-05/Dated 9/8/2017 NO EDN-H (PRY) (4) 9-16 dated 23/9/2017 | 12594-95 dated 1/9/2017 | Layout plan ,working drawing along with Specification issued vide letter no 2835-39 dated 15/11/2016 & 1286-90 dated 5/7/2017 & Revised Layout plan alongwith specification issued vide letter no 2133-36 dated 26/8/2017 | Revised A/A & E/S is awaited. |
| 15 | 6432 | C/O Govt Sr sec school Mandorghat Distt Shimla |  |  |  |  |  | Working drawing awaited. | _ |
| 16 | 6432 | C/o Science lab Govt sr sec school Basantpur Distt Shimla |  | 62801-02 dated 27/9/2016 |  |  |  | Layout plan ,working drawing along with standard Specification issued vide letter no 3316-19 dated 16/12/2016 | Estimate is being prepared. |

RURAL DHAMI, DIVISION, EDUCATION  (TEHSIL-SHIMLA RURAL)

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 17 | 6625 | Contour site plan proposed school building at Byachari | No. 243-244, dated: 26/12/2014 | No. 19672-73, dated: 27/12/2004 & No. /09-2252-55, dated: 12/02/2009 & No. /06- 16223-25, dated: 07/02/2006 |  |  | NO. 25142-43, dated: 09/02/2015 & No/ 2015-4082-84, dated: 07/01/2015 |  | Site not available due to Non-dismantling of old structure by client Deptt. |
| 18 | 6625 | Contour site plan proposed school building at Koh Bag |  | NO. 23890-92, dated: 02/02/2010 & No./ 06-16226-28, dated: 02/02/2006 & No./ 09-7848-50, dated: 30/07/2009 |  |  |  |  | _ |
| 19 | 6625 | Govt. Sr. Sec. School at Rampuri Keoanthal | No. E.D.N.-H (9)3-D.H.E., dated: 05/04/2012 | NO./ 09-16010-13, dated: 17/11/2008 & No. 109-20163-65, dated: 01/01/2009 & No. 13687-89, dated: 22/10/2009 |  | No. 2012/-1871-73, dated: 21/08/2012 |  | Ground floor & Ist floor completed. | 35% work completed. |
| 20 | 6625 | Sr. Sec. School Ghanahatti |  | No./09-20332-34, dated: 16/01/2009 | No./ 2013-3183-86, dated: 07/12/2013 |  | 13730-31 dated 14-9-2017 | Layout plan working drawing issued vide letter no 1973-75 dated 19-7-201 | Permission for dismantling has not being conveyed by the Education deptt. |
| 21 | 6625 | Govt. Sr. Sec. School Okhroo | No. E.D.N. –H(9)3-19/ 2008, D.H.E., dated: 02/12/2013 | 10047-48 dated 23/8/2016 |  |  | 13730-31 dated 14/9/2017 |  | On going work 10% work completed. |
| 22 | 6625 | Govt. Sr. Sec. School Shakrah |  |  | NO./ 478-87, dated: 05/05/2014 | No. E.D.N. –H (9)3-18/2008, D.H.E., dated: 30/05/2014 | NO. 5323-24, dated: 01/07/2014 | Working drawing issued vide letter no 5840-42 dated 28/7/2015 | 85 % work completed. |
| 23 | 6625 | C/o Science Lab. Govt. Sr. Sec. School Dhami |  |  |  | EDN-H (9) 3-18/2008 dated 28/10/2017 | No./ 14-25611-12, dated: 16/02/2015 | Layout plan working drawing along with specification issued vide letter no 2548-52 dated 19/9/2017 | 67% work completed. |
| 24 | 6625 | Govt. Sr. Sec. School Halog |  | No./ 14-5518-20, dated: 01/02/2014 8881-82 dated 11/7/2017 |  |  |  | A/A & E/S awaited of multipurpose hall. | - |

List of Works from 2005 4th Circle Education Theog

| Sr. No. | Job No. | Name of Project | Date of requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Remarks. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 25 | -do- | Up gradation of Govt. High School (Girls) to Sr. Sec. School (Girls) at Theog. | 48-49 Dated 16/5/2016 | Site plan received. vide letter No.9032-33 dt.28.12.04 --DO----- 5695-96 dated 2/7/2016 | Approval received vide letter No.EDN-H(9)3-6/04 dt.9.3.05 | Feasibility received vide letter No.373 -75 dt. 11.4.15 | Sketch drawings issued vide letter No.4708-09 dt.17.2.05 | Tender under process. |
| 26 | 6529 | C/O Govt SR sec school (Boys) Theog | No EDN –H(9) 3-19/2008 dated 28/12//2016 No EDN-H (9) 3-19/2008 dated 27-10-2017 | 18018-19 dated 8/2/2017 | EDN-H(9)-3/18/2008 dated 29/4/2017 | Working drawing approved vide letter No. 1313-17 dt. 10.7.17. | Layout plan ,working drawing Specification issued vide letter no 4843-46 dated 31/3/2017 | Tender under process. |
| 27 | -do- | Sr. Sec. School at Bagain. |  | Site plan received. vide letter No. 3803 dt. 26.7.2006 |  |  | Construction work doing under RMSA | On going work |
| 28 | -do- | Addl. Accommodation in GSSS Balag | Requirements received vide letter No.66-68 dt.10.7.06 | Site plan received vide letter No. 14014 dt. 30.3.2006 | Approval received vide letter No.EDN-H(9)3-2/07 | Feasibility received vide letter No.8528-29 dt.01.12.06 & Feasibility received vide letter No. 3756 dt. 16.7.07 | Layout plan & drawing Nos.259 & 260 vide letter No. 6432 (Referred drg.) issued vide letter No. 3087-90 dt.18.11.06 Revised layout plan & sketch drgs. issued vide letter No.1266-69 dt.23.6.07 W/drawings issued vide No.3776-78 dt.11.12.2007 Detail of toilets issued vide letter No.714-16 dt.14.5.08 Revised working drawings, detail of joinery & joints issued vide No.5376-78 dt.31.3.08 | - |
| 29 | -do- | Govt. Sr. sec. School at Deha (Sc. Lab.) | Requirement received from Principal Letter no 387 Dated30/11/2015 Requirement Received form Director Vide letter no EDN-H (9) 3-19/2008 18/12/2015 | - Site plan received vide letter No.7702 dt. 15.9.07 - Site Plan Received vide letter no 9066 Dated 5/11/2015 - Letter no 9066 dated 5/11/2015 | Approval received from Director Letter no EDN-H(9)3-18/2008 dated 27/12/2016 | Feasibility received vide letter No.9001-02 dt.02.11.07 3097-3100 dated 5/12/2016 20017-18 dated 18/3/2017 Requirement for feasibility report | Layout plan & w/drgs. of Sc. Lab. (standard design) issued vide letter No.3077-79 dt. 10.10.2007 Layout plan, Working drawing & Specification issued vide letter no 159-60 dated 18/4/2017 | -- |
| 30 | -do- | Govt. Sr. Sec. School at (Cheog) Sc. Lab. |  | Site plan received vide letter No. 1279-80 dt. 17.5.10 |  |  | Layout plan & w/drgs. of Sc. Lab. (standard design) issued vide letter No.2575-76 dt.16.9.10 | On going work |
| 31 | -do- | C/O Block Elementary Education office at Matiana (Theog) | No Shiksha – Sml(G-1)misc-2016 dated 17/12/2016 | Site plan received vide letter No.9439 dt. 11.8.11 | Approval received vide letter No.3938-39 dt.1.8.11 | Feasibility received vide letter No.2486-88 dt.24.6.11 | Drgs. issued vide letter No.1215-16 dt.23.6.11 Working drawing a/w specifications issued vide letter No.3002-04 dt.28.10.11 | On going work |
| 32 | 6529 | C/O Govt sr sec school Matiana theog distt, Shimla --New Govt Sr Sec School Building Matiyana Theog---- | 1365 dated 4/10/2016 | 7887-88 dated 3/8/2016 | EDN-H (9) 3-18/2008 dated 7/2/2017 | Feasibility 18605-06 dated 20/2/2017 | Layout plan, Working drawing along with specification issued Layout plan, working drawing allowing specification issued re- checking vide letter no 4719-21 dated 25/3/2017 | On going work |
| 33 | -do- | G.S.S.S.at Basadhar | Requirements not received from the Director Hr. Edu. | Site plan received vide letter No. 1094-95 dt. 7.5.10 Site plan received. vide letter No. 8395 dt. 20.12.11 | Working drawing & specification issued vide letter No, 159-60 dt. 18.4.2017. |  |  | Work started under RMSA ,drawing received from RMSA. |
| 34 | -do- | Govt. Sr. sec. School at Kiara Theog | Requirements received vide letter No.EDN-H(9)3-6/08 dt. 14.11.2011 | Site plan received vide letter No. 1256-57 dt. 18.9.10 --Do---- 15342-43 dated 20/12/2016 | Approval received vide letter No.EDN-H(9)3-18/08 dt.26.4.12 | Feasibility given to CA No. 20010-11 dt. 18.3.2017 20010-11 dated 18/3/2017 | Layout plan & sketch drawings issued vide letter No.5559-61 dt. 9.3.2012 Working drawing & Specification issued Vide letter no 159-60 dated 18/4/2017 | _ |
| 35 | 6529 | C/O Govt Sr Sec School Sainj Theog Distt Shimla | Requirement received from Principal vide letter No. 408 dt.92016 | 8337-38 dated 8/8/2016 |  |  | Working drawing issued for approval vide letter no 1551-54dated 27-7-2016 | Estimate under preparation.. |
| 36 | 6529 | C/O Shishu Kandara at Dhalli Shimla-6 |  |  |  |  | Working drawing issued vide letter no 4137-38 dated 15/2/2017 | On going work |
| 37 | -do- | C/O Govt. Sr.Sec.School at Mohori, Theog | Requirements received vide letter No.EDN-H(9)3-6/08 dt. 14.10.2013 | Site plan received vide letter No. 6032 dt. 05.9.13 | Approval received vide letter No.EDN-H(9)3-19/08 dt.21.1.14 | Feasibility received vide letter No.11395-95 dt.04.1.14 | Layout plan & sketch drawings issued vide letter No.3259-62 dt. 10.12.2013 W/drawings issued vide letter No.1940-42 dt. 04.8.2014 | _ |
| 38 | 6529 | C/O Govt SR Sec School Chanair Tehsil Theog New School Building Chanair Theog | No EDN/CHNR/ New School Building/285/2016-17 dated 19/11/2016 No EDN-H (9)3-19/2008 dated 23/1/2017 | Sent to CA vide letter No.12487-88 dt. 22.10.16. | EDN-H (9) 3-18/ 2008 dated 7/2/2017 | Feasibility report 20019-20 dated 21/3/2017 | Layout plan, working drawing along with specification issued | Working estimate under process. |
| 39 | 6529 | C/O Govt Sr Sec School Balsan Tehsil Theog | Received from Pri, No. 2016-17 dt. 21.11.2016 | Sent to CA vide letter No.9066 dt. 5.11.2015. | EDN-H (9) 3-18/ 2008 dated 7/2/2017 | CA No. 6529/2016 dt. 23.1.2017 |  | Tender under process. |
| 40 | 6529 | C/o Govt Sr Sec School Tyali tehsil Theog | No EDN(G-1) misc-2016 dated 17/12/2016 | 14212-13 dated 1/12/2016 | EDN-H (9) 3-18 / 2008 dated 7/2/2017 |  | Layout plan, Working drawing along with specification issued vide letter no 3895-99 dated 24/1/2017 | Tender under process. |
| 41 | 6529 | C/O Govt Sr Sec School Nahol Tehsil Theog | No EDN-Sml(G-1) misc-2016 dadted 17/12/2016 | 14214-16 dated 1/12/2016 | EDN-H (9) 3-18/2008 dated 7/4/2017 |  | Layout plan ,working drawing alongwith specification issued for approval | Tender under process. |
| 42 | 6529 | C/O Govt. Sr Sec School Kot- shilaroo Theog | No EDN (G-1)_misc-2016 dated 17/12/2016 | 641-42 dated 21/4/2017 |  |  | Layout plan ,working drawing &specification issued for approva vide No. 1583.87 dt. 25.7,17.l | Tender under process. |
| 43 | 6529 | C/O Govt Sr Sec School Kelvi Theog | No EDN (G-1)_misc-2016 dated 17/12/2016 |  |  |  |  | - |
| 44 | 6529 | C/O Govt Sr sec school Dharach Tehsil Theog | NO EDN-H(9)3-19/2008 dated 5/5/2017 |  |  |  |  | - |
| 45 | 6529 | C/o Govt Sr. sec school Sainj theog | Req. received from Pr.vide No. 408 dt.9.5.16 | Sent to CA vide No. 8337-38 dt. 8.8.16 | Working drg. Issued for approval vide No. 1551-54 dt. 27.7.2017. |  | Layout plan ,working drawing along with specification issued for approval Vide letter no 589-92 dated 24/5/2017 | Estimate under preparation. |

List of Work Education (Colleges) 4th Circle Shimla

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 46 | 7634 | Degree College at Theog |  | Site plan received for developing the ground & steps vide letter No.8141-42 dt.4.12.04 | Approval received vide letter No.EDN-H(9)3-10/04 Bldg. dt.9.3.05 | Feasibility report received E.E. Theog 576667 dated 25-7-2017 |  | Working drawing issued vide letter no 2049-51 dated 22/8/2017 | On going work |
| 47 | -do- | C/O Multipurpose Hall at Govt. College at Theog ---Science Lab Govt Degree College Theog | Requirements received vide letter No.EDN-H(9)3-9/08 dt. 7.4.15 | Site plan received vide letter No.8783-84 dt. 12.11.13 14398-99 dated 1/12/2016 | EDN-H (9) 3-9/2008 dated 10/1/2017 | Feasibility report received E.E. Theog 92-93dated 07-04-2017 |  | Layout plan & Sketch drawings issued vide letter no 34479-82 dated 23/12/2016 | On going work |
| 48 | 8009 | C/O Sanskrit College Building at Kiartoo Tehsil Theog | No. EDN-H(9)66-/2000(GC) Dated 3/2013 | Site plan received vide letter No. 439-40 dt. 29.5.12 | Received vide letter No. 2045-46 dt. 24.5.2014. | Feasibility received vide letter no 9591-92 dated 31-8-2016 | 2045-46 dated 17/9/2016 Letter received from E.E. Theog | Layout plan ,revised working drawing along with specification issued vide letter no 18609-10 dated 20/2/2017 | 80% work completed. |
| 49 | 8136 | State Library Building At Race View, Vidhan Sabha | No. EDN-H(9)3-19/2008 Dated 13/1/2015 Requirement No EDN-H (9) 3-19/2008 Dated 2/2/2015 No EDN-H (9) 3-19/2008Dated5/3-2015 | Site plan recived from E.E.Shimla Letter no 19997 Dated 22/12/2015 |  | EDN-H(9)3-18/2008 Dated18/12/2015 EDN-H (9) 3-18/2008 dated 12/9/2016 |  | Revised working drawing issued vide letter no. 4240-42 dated 18-02-2017 | On going work ,40% work done. |
| 50 | 8168 | C/O Sanskrit Academy Marahawag Tehsil & Distt Shimla Rural | No EDN-H (9) 3-19/2008 Dated 28/7/2016 | Contoured plan 24578 dated 14/2/2017 |  | EDN-H (9) 3-18/2008 Dated 23/8/2017 |  | Layout plan & working drawing issued for approval vide letter no 2058-61 dated 22/8/2017 | Approved working drawing awaited from concerned deptt. |
| 51 | 8184 | C/O Fine Art College Luharb Granm Panchyat Dudhalti Distt Shimla | EDN-H (9) 3-19/2008 dated 2/1/2017 | 17091-92 dated 211/11/2016 |  | EDN-H(9) 3-18/2008 dated 17/4/2017 |  | Layout plan , Working drawing issued vide letter no 4826-27 dated 31/3/2017 | Tender called. |

a List of Work Education (Other)I.T.I.  4th Circle Shimla

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 52 | 8030 | I.T.I. building at Jalog | 27592, dated: 10/05/2013 & 72175, dated: 26/09/ 2014 & No. 1533/-33, dated: 18/10/2014 & 35191 dated 10/5/2016 | No. / 014-5814-15, dated: 15/07/2013 & | No./ 2014=3142-45, dated: 03/1/2014 | No. S.T.V. (IT) HG (1) bldg./ Jalog, 2013-87012, dated: 26/11/2014 70505 dated 6/8/2016 | No./ 14- 19042-44, dated: 15/12/2014 | Layout plan & working drawing along with specification issued vide letter no 295-98 dated 25-4-2016 | Work awarded to the contractor. |
| 53 | 7857 | I.T.I. Shogi (Sonu Bonglow )Distt Shimla |  | No 24253-54 Dated 20/10/2015 From E.E.Rural Division Dhami |  |  |  |  | Site not available. |
| 54 |  | C/o Skill upgradation center and Professional Training Center (COE) in Gram Panchayat Anandpur Distt Shimla |  |  |  |  |  |  | __ |
| 55 | 8182 | C/O Polytechnic College at Basantpur Distt Shimla |  | 18139-40 dated 29/11/2016 |  |  |  |  | Land not handed over to client deptt. |