List of works Mandi (GAD) 1st  circle

| Sr.No | Job no. | Name of Work | Date of requirements received | Date of receiving site plan & details | Date of approval | Datof feasibility | Status of projrct | Status Supplied by SE. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 7130 | Residence for mentally challenged children at sundarnagar |  | *30.3.17 |  |  | *letter issued to EE Sundarnagar for the detailed contour site plan and requirements from the concerned department on dt. 7.4.17 | - |
|  | Mz-380 | Beautification and improvement of roundabout at Gandhi chowk & development of Chowk & Park near ITI Mandi |  |  |  |  |  | Work is in progress. |
|  | MZ-299 | Landscaping development plan at Shiv-Mandir at Nagchala | 31.5.2008 | 31.5.2008 | --- | --- | Drg. Issued on dt5/6/08 | - |
|  | CZ-146 | M.c toilet block and rain shelter for M.C Mandi near new Suketi bridge. | 21.9.2010 | 21.9.2010 | -- | -- | Drg. Issued. On 30.10.10 | Work completed. |
|  | 3927 | Mini secretariat Sundarnagar Litigant cell | 29-5-2012 | 29-5-2012 | 6-7-2013 | 7-12-2012 | Drg issued in dt 7.6.11 *issued on dated 6.7.11 *drgs issued on dt.19.7.11 |  |
|  | 6609 | Sunken Garden (Shopping Complex ) at Mandi H.P * Planning of shops | 23-1-2012 |  |  |  | Letter issued to Executive officer Municipal Council Mandi H.P vide letter no 2583-86 dt 15.2.12 for the detailed site plan Drg.issued. *sketch drgs issue dt. 9.2.17 | Work completed. |
|  | Cz-342 | Provision of Electronic Voting Machine (E.V.M) ware-house. | 27-1-2011 | 27-1-2011 |  |  | *issued on dt.7.02.2011 in person. | Approval awaited . |
|  | 3251 | Deputy commissioner building Mandi |  |  |  |  |  |  |
|  |  | * provision of Parking | 28.08.2009 | 28.08.2009 | --- | -- | *re issued on.dt7.2.10 | Feasibility & approval awaited |
|  |  | c/o of light weight pre- fabricated structure and multipurpose hall Over DC OFFICE | 5-3-10 | 5-3-10 | -- | -- | *Drgs already issued vide letter no 27.7.10 *drgs reissued on dt. 26.2.13 *drgs issued vide on dt. 7.6.14 | Feasibility & approval awaited |
|  |  | *Rehri Market and unloading yard at By-Pass (NH) Mandi |  | 17.4.13 |  |  | *sk drg issued on dt. 26.4.13 vide letter no84-89 *sk drgs reissued on dt 20/5/13 vide letter no. 127-32 | - |
|  | Cz-123 | REST HOUSE AT SANDHOLE | 28.03.2006 | 28.03.2006 |  | 23.1.2007 | Working dwg Issued on dt 14.3.07 | Pertain to Joginder Nagar Circle. |
|  | Mz-191 | *Zila Sainik Welfare Mandi. * Office building and living accommodation for Army recruitment office Mandi. | 21.07.2000 18.10.2011 | ---- | --- | --- | -- | Requirement & site data awaited from director sainik welfare deprt. Hamirpur vide office dt 2.11.11 |
|  | Mz-353 | New Bus Stand Complex at Karsog (HP) | --- | 28.12.11 | ----- | ----- | Letter issued to The Managing Director H.R.T.C. Shimla HP dt 15.2.12 | ******** Requirement awaited |
|  | Mz-359 | C/o community hall at Kangoo in Gram Panchayat Kangoo. | 22.6.12 | 22.6.12 | -- | 21.3.13 | sketch. 12.7.12 vide Working drgs issued to EE Sundarnagar on dt. 23.4.13 |  |
|  | Mz-102 | Food and supply Deptt. (standard laboratories) | 8.1.13 | 9/1/13 | --- | ---- | sketch. drgs issued wide letter no. 388-93 on dt. 23.8.13 | Feasibility & approval awaited |
|  | CZ-363 | Multi-purpose hall in the premises of paddal stadium ground. | 6.3.13. | 6.3.13. |  |  | * drgs issued on dated 7.3.13 vide letter no. 2291-96. | ***** |
|  |  | *development of paddal ground | 6-01-2015 | In person dt 6-01-2015 |  |  | *drawing issued vide letter no. 1303-1307 dt. 16.01.15 | Work completed. |
|  | Mz-367 | Balh sadhan at Dadour. | 9.5.13 | 9.5.13 |  |  | *drgs issued vide letter no. 390-93 on dt. 4.7.14 | ***** Approval & feasibility awaited |
|  | 4578 | Sub-Jail at Mandi |  |  |  |  |  |  |
|  |  | * Type-II Qtrs. |  |  |  |  | *Drawing issued on dt 20-5-10 | Work completed. |
|  |  | *construction of parking-cum-commercial complex. |  |  |  |  | *letter issued to the Director General Of Prisoners(H.P) vide letter no. 1748-55 dt.28.7.11 *letter issued to E.E Mandi div.II mandi vide letter no 2786-90 dt 26.3.12 *letter issued to EE Mandi-II on dt. 26.4.13 vide letter no. 79.83 | Site not handed over. |
|  |  | *Sub-jail Behna | 12-6-2012 | 1.8.12 vide 4-11-2011 |  |  | *letter issued to Chief Architect HPPWD Mandi on dt.11.9.12 *conceptual drg issued for approval on dt. 24.9.12 vide letter no. *letter issued to EE Mandi –II vide letter no 953-60 on dt. 9.11.12 *letter issued to the Additional Director General (prisos) HP Shimla vide letter no. 2079-84 dt. 11.1.13 *drgs issued on dt. 1.2.13 vide letter no. 4298-4307 form the office of chief architect Shimla. | Shifted at Batahalari near Ner-Chowk. |
|  |  | *Central jail Mandi at Batahalari near Nerchowk |  | *New. site plan 26.6.14 & re submitted dt. 20-01-2015 |  |  | 2*letter issued to EE Mandi-II for the complete site data of the proposed site vide letter no. 365-69 on dt. 3.7.14 *letter issued to EE Mandi-II vide letter no. 733-36 on dt. 10.9.14. *letter issued to The Deupty Commissioner, Mandi vide letter no. 831-35 on dt. 14.10.14 ( contoured site plan still awaited.) *Letter issued to The Sr. EE Elect. Div. HPSEB , Ltd. Sundarnagar vide letter no. 1060-63 dt. 15.11.14. *letter issued to The Deputy Commissioner Mandi on dt. 6.7.15decision of the land. | Site not handed over by the client department. |
|  | Cz-123 | Add. Accommodation on first Floor of rest house at Chatri distt Mandi | 8-9-2008 | 8-9-2008 |  | 16-6-2009 | Drawing issued on dt 09-6-09 | Detailed estimate under process. |
|  | Cz-123 | Rest House/Gang hut at Galma distt Mandi | 23.2.2010 *11.5.17 | 23.2.2010 *11.5.17 *7.7.17 |  | 29.3.2010 | Drawing issued on dt 17.11.11 vide letter no 2190-95 | Roofing work is in progress. |
|  | Cz-123 | Rest house at thachi distt. Mandi. | 07.10.2009 | 07.10.2009 | ----- | 21.10.13 * | Issued on dt dt. 28.2.13 *Revised drgs issued on dt. 4.2.14 | Work is in progress and all drawings received. |
|  | Cz-162 | Existing type-IV qtrs near vishwakarma temple Mandi | 23-10-2011 | 23-10-2011 |  | .6.7.11. | Working dwg issued on 26.4.11. | A/A & E/S awaited. |
|  | Mz-348 | A.E OFFICE & TREASURY BUILDING AT BALI CHAWKI. | 21.04.2011 | 21.04.2011 | 21-02.2012 | 29.7.2011 | *working dwg issued on 6.2.14 | Structure drawing of first floor top beam & slab and second floor trusses with joinery details required. |
|  | 5009 | Add.acc. for Circuit house Mandi | 12-05.2015 | 12-05.2015 *14.7.15 *13.7.15 (guard hut & store) | Yet not recieved | 7.10.15 | Working Drgs. Issued on dt. 25.6.14 *drgs issued dt. 29.6.15. *letter issued to EE mandi on dt. 20.11.15 *letter issued to EE Mandi-II on dt. 12.5.17 | Work awarded to the contractor and site development work is in progress. |
|  | 5009 | NEW SITE FOR CIRCUIT HOUSE AT KANGNI, DISTT. MANDI | 12.7.13 | 12.7.13 |  |  | Scheme under consideration | ***** |
|  | Cz-162 | Transit accommodation for PWD staff at Paddle Mandi | 12.4.12 | 12.4.12 | -- | 29.10.14 | Skt drgs issued on dt. 23.9.14 *working drs issued dt. 3.9.15 | Land dispute. |
|  | Cz-298 | Divisional office bldg at Karsog HP.PWD. Karsog Distt. Mandi. | 13.05.08 | 13.05.08 | Std drawings adopted | 09.09.2008 | Working Drg. Issued on dt 19/7/08 | Work is in progress. |
|  | Mz-128 | Additional. Accommodation. For inspection hut/ rest house at Dehar | 29.6.12 | 29.6.12 | --- | 4.10.12 | *drgs issued on dt.30.8.12 vide letter no.753-56 | Approval awaited |
|  | MZ-295 | Construction of div. office building gohar. | 21-5-2008 |  |  | 10-2-2009 | *issued on dt. 9.7.13 | Completed. |
|  | Cz-262 | Construction of type-II quarter for PWD staff at Sundarnagar |  | 1.8.13 |  |  | * LAYOUT PLAN on 19.3.14 *drgs (type-II) issued vide on 29.3.14 | Work in progress. |
|  | MZ-258 | Mini-sectt. At karsog | 19-03-2015 *2.11.15 *1.2.2016 *04.01.2016 | 19-03-2015 In person *22.4.2015 *7.10.2015 *section received dt. 28.11.15 | *16.04.2016 | *8.4.16 | *layout plan & sketch drgs on dt. 25.4.15. *letter issued to Ee Karsog on dt 19.05.15 for the complete site plan of the site. *letter issued on dt. 4.6.15 for the complete site information. *letter issued on dt. 4.7.15 for the detailed site plan and branch wise requirements of accommodation. *letter issued on dt. 12.10.15 for the detailed site plan still awaited. . sketch drgs issued on dt. 9.2.2016 *working drg issued dt. 25.4.16 | ***** |
|  | 7085 | State vigilance and anti corruption bureau office building at ram nagar Mandi (hp) | 2.1.14 | 2.1.14 | --- | 27-8-14 | Sketch drgs issued dt. 29.1.14 Working drgs issued on dt. 14.3.14 | A/A & E/S awaited. |
|  | Mz-375 | Mini secretariat building at Nerchowk Mandi H.P. | 8.1.16 *9.5.16 | 4-1.2014 *10.2.14 *revised dt. 13.01.16 *revised dt. 17.6.16 | 31.3.17 | 21.2.17 | *letter issued 13.2.14 for the requirements. *drgs issued on dt. 17.2.16 Drgs. Issued to d.c for approval on dt14.2.17 | A/A & E/S awaited. |
|  | Mz-204 | Office building for SMS /HDO and HEO at Sundarnagar. | 21-10-2013 | 03.2.14 5.7.16 from e.e | 5.11.15 | 22.8.15 | sketch drgs drgs issued vide letter no. 1036-40 on dt. 10.2.14 drgs.issued for approval on dt. 9.10.15. working drgs. Issued on dt. 10.6.16 & also on 16.7.16 | Work is in progress. |
|  | Mz-379 | Shri Panchvaktra temple Mandi | 23-04-2014 | 23.4.14 |  |  | Sketch drg.issued vide letter no. 247-52 dt. 19.6.14. | *letter issued to EE Mandi-II vide letter no. 443-47 on dt 11.7.14 ( for marking HFL on the proposed site) |
|  | Mz-381 | Parking near Tehsil office building at Mangwain Mandi | 29-04-2014 | 29-04-2014 |  | *feasibility received from EE Mandi-II vide letter no. 6200-01 dt. 23.6.14 & dy. No. 133 dt. 27.6.14. | *drg issued vide letter no. 205-209 dt. 16.6.2014 | Land not available. |
|  | 7045 | C/O Kids swimming pool at Bhiuli ,Mandi | 16-06-2014 | 27-05-2014 |  | Sketch drg. | * drg issued vide letter no. 215-219 dt. 17.6.2014 | Work completed. |
|  | 7085 | C/O S.P.SV & ACB Central Range Mandi (Residence Building) |  | 23.6.14 |  | *3.6.17 | *letter issued to S.P SV & ACB Central Rande Mandi vide letter no. 190-94 dt. 12.6.14 (site plan still Awaited) * drgs issued dt. 31.7.14 *letter issued to EE Mandi-II dt. 02.09.2014 *drg issued dt2.2.17 | Working estimate is under preparation. |
|  | Mz-363 | Sanskriti sadan at Motipur Mandi | 20.3.14 | 20.3.14 | 22.12.16 | 26.7.15 *25.5.16 | *drgs issued dt. 29.7.15 *w/drg. Issued dt. 15.2.17 | Work awarded to the contractor by the EE Mandi Division No.II vide letter No. 23751-59 dated 04-10-2017. Structural drawings submitted to the Chief Engineer on dated 07-03-2018 for approval. Revised Tatima of land domarcated at site and revised digital map under preparation for correction in FCA case. |
|  | Mz-363 | Indoor Stadium at Motipur Paddel Mandi | 10.10.14 | 20.3.14 |  | Sketch drawing | *drawings iddued vide letter no. 1259-63 on dt. 7.1.2015 | ***** |
|  | 385 | MT Godown under MANREGA at Thunag | 10-09-2014 | 10-09-2014 |  |  | *letter issued to Chief Architect vide letter no. 420-23 on dt. 9.7.14 ( request for the supply of standard drgs. Of 200 MT Godowns ) | - |
|  | Mz-386 | Stadium at Baldah village Chaloh P.O Saigalu Kotli | 20.11.14 | 20.11.14 |  |  | Layout plan | Insufficient site. FRA under process. |
|  | 7640 | Sub-Tehsil Building at Bhadrota , Sarkaghat. | 7.8.14 | 7.8.14 |  | 17.8.16 | Drgs issued on dt. 11.5.15 vide letter no. 84-88. 5.7.16 letter issued 28.7.16 drgs. Issued for approval | A/A & E/S received. |
|  | CZ-229 | BUS-STAND MANDI TOILET BLOCK. | 24.6.14 *18.4.17 (color scheme) | 24.6.14 | 17-07-2014 | *feasibility received from Ee Mandi-II vide letter no. 8821-22 dt. 17.7.14 & dy. No. 184 dt. 19.7.14. | DRG Handedover OVER TO A.E CONCERN IN PERSON ON DT. 16.6.13 & 17.9.13 *drgs issued vide letter no. 394-99 on dt. 4.7.14. *drawings issued vide letter no. 1072-77 on dt. 18.11.14. *working drgs issued dt.9.9.15 *detail of flooring pattern issued dt. 25.4.17 | Not pertain to this department. |
|  | 4850 | Divisional commissioner office Mandi (type qtrs) | 23.4.15 | 23.4.15 | -- | --- | Letter issued on dated 12.03.15 along with cross sections. | A/A & E/S awaited. |
|  | 8058 | Stadium at Sandhol. | 29.10.14 | 29.10.14 | 16.5.16 | 30.12.14 | *Sketch drg issued in dt. 18.11.14. *working issued drawings dt. 21.5.15 | Pertain to Joginder Nagar Circle. |
|  | 7085 | C/O Police VHF Repeater Station at Naina-Deviji Tehsil Balh , Distt. Mandi. |  | 23.10.17 |  | 21.1.15 | w.DRGS ISSUED DT. 21.11.15 | Work is in progress. |
|  | Cz-289 | Fire station at Jhamar , Mandi | 18.4.15 | 18.4.15 | --- | 4.2.16 | Sketch drgs issued on dt. 24.4.15 *letter issued to The Commander (Home Guard) 6th Battalion Mandi. On dt. 23.2.16 * working drgs issued vide letter no. 121-125 dt. 28.4.16 | Work is in progress. |
|  | Mz-395 | Company commander home guard and fire brigade office at Karsog. | ---- | 20.6.15. | --- | --- | --- | Does not pertain to Karsog Division. It pertain to BDO office Karsog. |

| 48 | 4403 | c/o AE office at Kotli | 11-06-2015 | 11-06-2015 | --- | --- | W.drgs issued | Land is not available. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 49 | Mz-403 | Sainik sadan Sainik Rest House complex Mandi. | _ | 7.04.2016 | _ | - | *letter issued to EE Mandi-II for the Appropriate site data as well as requirements . | Land is not available. |
| 50 | Cz-146 | Shelter for Urban Homeless in Mandi. | 27.5.16 | 27.5.16 | 21.7.16 *19.7.17 |  | Sketch drgs issued dt. 1.6.16 | Site not handed over. |
| 51 | Cz-231 | Bus stand sarkaghat | 18.1.16 |  |  |  | Lettr issued to Chief Architect regarding status of the project in dt. 19.01.16 |  |
| 52 | MZ-399 | Panchayt Ghar Sehali | 1.10.15 *19.10.15 | 29.8.15 | 25.2.16 from Distt. Panchayat officer Mandi |  | Letter issued to EE Mandi-II for the requirements and photograph of the site on dt. 29.9.15 *drgs issued dt. 1.02.2016 *joinery detail issued dt. 12.4.16 | 90% work is completed and finishing work is in progress. |
|  | MZ-399 | Panchayt Ghar Bhargoan | 1.10.15 *19.10.15 | 29.8.15 | 25.2.16 from Distt. Panchayat officer Mandi |  | Letter issued to EE Mandi-II for the requirements and photograph of the site on dt. 29.9.15 *drgs issued dt. 1.02.2016 *details issued dt. 22.4.16 | Work completed. |
|  | 6609 | Re-construction of Kargil Park Mandi | 22.6.15 | 22.6.15 |  | 3.5.15 | *drgs issued dt. 30.1.16 *working drg issued dt. 28.5.16 *drgs re-issued dt. 8.7.16 *letter issued to D.C Mandi dt. 30.11.16 | Approval awaited from client department. |
|  | CZ-230 | A.E Office cum Residence at Rewalser. | 4.9.15 | 4.9.15 |  |  | Std . drgs issued In person | Land is not available. |
|  | Cz-265 | HPPWD Sub-Division at dehar. |  | 15.12.15 |  |  | *letter issued to EE Sundarnagar for the photographs and drawings of the existing JE Residence on dt. 19.12.15 | Estimate under process. |
|  | 4792 | Type-III or Type-II residential building district treasury office Mandi. | 6.7.15 * | 6.7.15 *1.11.16 |  | 8.01.16 *29.2.16 *7.9.16 | Layout and sketch drgs issued on dt. 24.11.15 *working drgs issued dt. 2.2.16 *revised drgs issued dt. 9.6.16 | Feasibility report submitted by the EE Mandi-II vide letter No. 3712-13 dated 06-05-2016. |
|  | 4792 | Sub treasury office at Chachiot , Gohar | 28.11.15 | 28.11.15 | 29.2.16 | 8.3.16 | Sketch drgs issued dt. 21.1.16 *w/drg issued dt. 7.3.17 | Work awarded to the contractor. |
|  | 4792 | Departmental building at Deputy Director / Distt./ Sub-Treasury Offices. | 7.12.15 | 7.12.15 |  | 6.5.16 | Sketch drgs issued dt. 2.2.16 | Working drawing awaited. |
|  | 415 | Hot water pool near Laxmi Narayan Temple at Tatapani , Karsog | 25.7.16 | 25.7.16 | 6.2.17 | 10.3.17 | Drg issed dt. 20.1.17 *working drgs issued dt. 21.6.17 | - |
|  | 7526 | Additional accommodation at SE Office 1st circle HPPWD mandi | 2.7.16 | 2.7.16 |  |  |  | Preliminary estimate submitted to the E-in-C office vide CE(MZ) office letter No. 22437-40 dated 02-02-2018 amounting to Rs. 71,05,000/-. |
|  | 162 | Type-II Qtrs PWD Colony rewalsar |  |  |  |  | *joinery detail issued dt. 7.11.14 | Work is in progress. |
|  | 162 | Zila parishad office building Jail road mandi (conversion into residential purpose) |  |  |  |  | Sketch drg issued dt. 28.8.15 | Not constructed by this department. |
|  | 424 | Press club building Nerchowk | 23.12.16 | 26.12.16 Letter no. 31297-99 dt 23.12.16 *existing plan and photographs letter no. 35753-54 dt. 4.1.17 *9.1.2017 |  |  | *drgs issued 31.01.2017 | Preliminary estimate submitted DPRO vide EE Mandi-II office letter No. 19051-54 dated 29-08-2017 for Rs. 24,23,300/-. |
|  | 7085 | TYPE-II QUARTERS AT POLICE RESIDENTIAL COLONY AT DHANGSIDHAR MANDI | 11.1.16 21.1.16 | 8.11.16 |  |  | Drgs issued. | Work completed. |
|  | 4792 | Treasury office building at baldwara disstt. Mandi | 18.2.2 017 | 27.02.2017 | 12.6.17 | 21.4.17 | Letter issued for requirements on dt. 4.3.17 Drgs issued dt. 28.3.17 *letter issued to EE Sarkaghat on dt. 4.5.17 Working drgs. Issued on dt. 6.10. 17. | - |
|  | Mz-399 | Panchayat Bhawan at Sarkaghat |  | 23.5.17 |  |  | *letter issued by EE Sarkaghat on dt. 2.6.17 for the requirements to be housed in the building. | - |
|  | 6609 | Municipal Committee office building Mandi |  | 02.01.17 | 13.2.17 | 14.2.17 | *drgs issued dt. 09.2.17 *drgs reissued dt. 17.2.17 *drg issued dt. 25.5.17 | Approval of drawings awaited from the client department. |
|  | 6609 | 2 NOS. SHOPS AT SERI BAZAR MANDI | 3.12.16 | 3.12.16 |  |  | DRG ISSUED DT. 2.8.17 | Not pertain to this department. |
|  | MZ-431 | Residential building for mentally challenged children s/nagar distt mandi (HP) |  | 29.7.17 |  |  |  |  |
|  | Mz-427 | Excise and taxation office at sarkaghat distt. Mandi (HP) | 19.1.17 | 19.1.17 |  | 2.5.17 &22.5.17 | Drgs issued dt. 24.4.17 | Work is in progress. |
|  | MZ-123 | Rest house at Janjehli | 24.8.17 | 24.8.17 |  |  |  |  |
|  | MZ-123 | Rest house at sarkaghat (additional accommodation) | 19.7.17 | 19.7.17 |  |  | *letter issued to EE sarkaghat for the detailed plan of existing rest house.dt. 3.6.17 | Contour site plan sent to the Senior Architect Mandi Zone and necessary working drawing awaited. |
|  | MZ-123 | Rest House at Sudhar (additional Accommodation) | 6.7.17 |  |  |  | *drgs issued dt. 4.9.17 | Working drawing has been prepared and estimate is under preparation. |
|  | MZ-123 | Rest House Gulma | 7.7.17 | 7.7.17 |  |  | *letter issued to EE Mandi-II dt. 11.9.17 for the existing roof plan. | Roofing work is in progress. |