| List of Work (Other) vetinary 12th Circle Nahan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Remarks |
| 1 |  | C/o Veterinary Hospital at Deed Bagar tehsil Nahan |  | 576-77 dated 13-7-2017 |  |  | Letter issue for detailed requirement vide letter no 2860-63 dated 24/10/2107 | Leter issue to Director Animal Husbandry for detailed requirement vide Chief Architect Shimla letter No. 2860-63 dated 24-10-2017 but the same is still awaited. |
| 2 |  | C/o Veterinary Dispensary Parada Nahan |  |  |  |  |  | Letter issue to Chief Architect P.PWD. Shimla vide Deputy Director Animal Husbandry Distt. Sirmour letter No. 5482 dated 16-11-2017 for issue the drawing No. 9 Job No. 4145 which is still awaited from Chief Architect and the concerned deptt. Want to constructed this building as per above mentioned drawing. |

| List of work (Other)Stadium/Auditorium 12th Circle Nahan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No | Job No. | Name of Project | Date of requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Remarks. |
| 3 | 8210 | C/o indoor Auditorium Nahan | No Bhasni -02 /2007 dated 7187 dated 26-7-2017 | Contour Site Plan received 574-75 dated 13/7/2017 | ---- | ----- | letter no 1686-89 dated 29/7/2017 issued to The Director Language & culture Department HP Shimla -9 | Contour site plan has been submitted to Chief Architect HP.PWD., shimla For evolving the working drawing but the same is still awaited. |
| 4 | 4437 | C/O Indoor stadium Nahan/Shooting ‘range ‘at Nahan ---DO— Indoor Shooting Range at Nahan | 52-54 dated 18/4/2016 2070-73 dated 28-2-2014 |  | 1975 dated 7-7-2011 dated 7/4/2016 | 1748-51 dated 21-5-2011 | Revised working drawing issued vide letter no 4496-99 dated 9/3/2017 | Revised estimate for 10 mtr. indoor shooting range sent to Chief Engineer(SZ) vide t/o letter No.2241-42 dated 18.7.2017 for Rs.111.11 lakh for accord of revised A/A &E/S but the same is still awaited. |
| 5 | 4437 | C/O Indoor stadium Nahan/Shooting ‘range ‘at Nahan ---DO— Indoor Shooting Range at Nahan | 52-54 dated 18/4/2016 2070-73 dated 28-2-2014 |  | 1975 dated 7-7-2011 dated 7/4/2016 | 1748-51 dated 21-5-2011 | Revised working drawing issued vide letter no 1496-99 dated 9/3/2017 | Revised estimate for 10 mtr. indoor shooting range sent to Chief Engineer(SZ) vide t/o letter No.2241-42 dated 18.7.2017 for Rs.111.11 lakh for accord of revised A/A &E/S but the same is still awaited. |

| List of Work(Other) Rest House 12th Circle Nahan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Job. No. | Name of Work | Date of Requirement. | Date of Site Plan. | Date of Feasibility. | Date of Approval | Status of Work | Remarks. |
| 6 | 4464 | Rest house at Nohradhar distt. Sirmour. |  |  |  |  | Working drawings with specification sent to EE, Sangrah Div. Vide letter no 2882-83 dated 17/11/2016. | Drawings received from chief Architect and estimate is Under Prapartion. |
| 7 | 4060 | Rest house at Rajgarh. |  |  |  |  | Working drawings with layout& Specification sent to EE, Rajgarh division vide letter no 2047-48 dated 17/09/16. | Land not finalized by the land owner so far. |
| 8 | 3509 | Regarding C/O dining room, sitting room and VIP suit along with stair hall on the second floor of rest house at dadahu distt. Sirmaur. |  |  |  |  | EE, Nahan div. requested to Approval vide letter no 1682-85 dt. 29/07/2017 | As intimated by the Chief Architect Shimla vide letter No. 1682-85 dated 29-7-2017 that Additional accommodation cannot be provided without the approval of Cabinet which is not available. |
| 9 | 7650 | C/O rest house at Nainiadhar . |  | Vide letter no 5774-75 dt. 01/09/2012 |  |  |  | Land available but no funds available |
| 10 | 7650 | C/O rest house at jadol Taproli Tehsil Rajgarh distt. Sirmour. | Vide letter no 8192-93 dt. 03/10/2017 | Vide letter no 8113-15 dt 28-09-17 |  |  | EE, Rajgarh is requested for detail requirements vide letter no 2643-46 dt. 03/10/17 Drawings to be revised. | Land not finalized by the land owner so far. |

r

| List of Work(Other) PWD Nahan Circle |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Job No. | Name of Project | Date of requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Remarks |
| 11 | 3183 | C/O AE. Office& residential accommodation for HPPWD Employees at Nohradhar. |  | Vide letter no 1527-29 dated 01/06/15. |  |  | Layout plan & working drawing issued to EE, Sangrah div. vide letter no 1458-60 dt. 20/07/15. | Due to decelation of National High way of solan meenus road. The site proposed for said accommodation is now not feasible.Hence the afforts being made for arranging of new site. |
| 12 | 3183 -do- -do- | A.E. office & Residence accommodation for PWD Employees at Nohradhar -do- -do- Reminder Letter from E.E. received (No. 1527-29 dated 01-6-2015) | 3428-29 dated 15-7-2014 (Req. from E.E.) | 8755-56 dated 20-12-2014 |  |  | 1819-21 dated 26-7-2014 Layout plan issued to EE, Sangrah Division vide letter no 1458-60 dated 02/07/15. | Due to decelation of National High way of solan meenus road. The site proposed for said accommodation is now not feasible.Hence the afforts being made for arranging of new site. |
| 13 | 3183 | C/O Office cum-residential building for asstt. Engineer. At Haripurdhar distt. Sirmour. |  |  |  |  | EE, requested to supply contour site plan vide letter no 1767 dt. 03/08/2017 | Estimates for arranging of A/A & E/S is stand submitted to Additional chief Secy (Public works) to the Govt of H.P.vide CE Shimla Zone office letter No. 3495-96 dated 14.08.2016.But A/A &E/S still awaited |

| List of Work(Other) Police Deptt. 12th Circle Nahan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Job No. | Name of Project |  |  |  | Date of requirement received |  | Date of receiving site plan & details |  | Date of approval |  |  | Date of feasibility |  | Status of project |  | Remarks. |  |
| 14 | 5003 | Police Thana at Kala Amb -do- |  |  |  | Letter No. 13606 on dated: 19-3-2015 |  | 6847 dated 18-3-2015 27-28 dated 2-4-2015 (from S.E.) |  |  |  |  | 279-82 dated 23-5-2015 |  | Letter no 2284-86 Dated 07/09/2017 Joinery details,Detail of doors &window joints, detail of grill door in lock-up sent to EE,Nahan Division HP, PWd, Nahan vide letter no 2284-86 dt. 07/09/2017 |  | Work is in progress. |  |
| 15 | 4626 | New Builidng of Police Thana at Poanta Sahib ---do--- |  |  |  | 3132-34 dated 25-8-2014 ( Requirement for Parking Facility) 2561 dated 28-01-2015 ( rationalized requirements) |  | 2485-88 dated 25-7-2014 3438-40 dated 2-9-2014 (Received Measurement DRG. of Exist. Building & Photos) |  |  |  |  |  |  | approvad. Working drgs. issued to EE, paonta Sahib div. vide letter no 5063-64 dt. 23/02/2016 |  | 45% work completed. |  |
| 16 | 5003 | C/O 6 Nos type II qtr at police colony Devi nagar poanta Sabib. |  |  |  |  |  | Vide letter no 1664 dt. 08/03/2017 |  |  |  |  |  |  | Layout plan working drgs. issued to EE Poanta Sahib division vide letter no 1588-91dt. 25/07/2017 |  | Tender called which is due to be opened on 22-2-2018. |  |
| 17 | 7103 | Police Line Nahan. |  |  |  |  |  |  |  |  |  |  |  |  | From SE 12thCircle HPPWD, Nahan. Vide lt. No 6040-41 dt. 28/03/2016 |  | Feasibility report has been submitted for multistory building in police line at Nahan S.E.12th office letter No. 6040-41 dated 28-3-2016. Now the construction work on this building is in progress. |  |
| 18 | 7103 | Police station and residences of PS.SV&ACB,Nahan distt. sirmour |  |  |  | Received from (Mohit Chawla),IPS Superintendent fo police SV&ACB,SR,Shimla -2. On dated25/04/16 |  |  |  |  |  |  |  |  | Drawings issued to ADG SV&ACB HP. Shimla-2 for approval vide letter no 1548-50 dt. 27/07/16 |  | Residences for staff of PS,SV&ACB are not proposed at Nahan. |  |
| 19 |  | C/O Police station SV&ACB at Nahan.Under modernization os state police force scheme. |  |  |  |  |  | From EE Nahan Div. HPPWD, Nahan vide letter no 56-59 on Dt 18/04/16. |  | Vide letter no 17818 dt. 26/08/2017 |  |  |  |  |  |  | Tender open on dated 1.2.2018 is being scrutinized in division office which will be submitted to higher office for finalizing. |  |
| 20 | 7103 | New multi-storey building at Police line Nahan distt. Sirmour. |  |  |  |  |  | Received from EE, Nahan 5897-99 dt. 10/08/15. |  | Vide letter no 5604/02/03/16 dt. 02/03/16 |  |  | Vide letter no 4882-84 dt. 11/03/16 From SE 12th circle vide letter no 6040-41 dt 28/03/16 |  | Layout plan,working drawing with specification issued to EE,Nahan Division vide letter no 1897-98 dated 03/09/16. |  | Work is in progress. |  |
| 21 | 7103 | C/O type-II quarters(standard Design) Police station complex at Renukaji. |  |  |  | From DGP HP vide letter no 9054 dt. 06/04/15. |  | Received. From EE, Nahan Div. vide letter no 4596-98 dt. 19/01/2016. |  |  |  |  |  |  | Joinery (Doors& windows etc. demanded by EE, Nahan div. vide letter no 544-46 dt. 01/07/15. |  | Work awarded to the contractor but not started by him so the work rescinded and tender for the same were recalled and opened on 1.2.2018which will be sent to the higher authority for finalizing |  |
| 22 | 8148 | C/o Fire Brigade Station at Paonta Sahib Distt. Sirmour |  |  |  | Received from J.C. Sharma Chief Fire Officer HP Shimla-2 on dated 25/04/2016 |  |  |  |  |  |  |  |  | Letter No. 1084-88, dated: 24.06.2016 Letter send to Director General Cum-Comandant General Home Guard/Civil Defence, HP for approval |  | Tender called which is due to be opened on 8-2-2018. |  |
| 23 |  | C/O Fire Post building at Kala Amb. Distt. Sirmour. |  |  |  | Received vide letter no 7869-72 dated 03/10/2016 |  | Vide letter no 1612-14 dated 27/01/2017 |  |  |  |  |  |  | Working drawings with specification issued to the DG-cum-Director fire services, HP Shimla vide letter no 4317-20 dated 27-02-2017. |  | Tender called and will be opened on dated 6.3.2018. |  |
| List of Work (Others )12th Circle Nahan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sr. No. | Job No. | Name of Project |  |  | Date of requirement received |  | Date of receiving site plan & details |  | Date of approval |  |  | Date of feasibility |  | Status of project |  | Remarks. |  |
| 24 | 8129 | C/O ETO Poanta Sahib, distt. Sirmour HP. |  |  | From Excise &Taxation Officer Poanta Sahib, distt, Sirmour HP. Vide lt. No.177 on dated 17/03/2016 |  | Vide letter no 5751-53 dated 12/01/17 |  |  |  |  |  |  | Drawings sent to The escise & Taxation commissioner, HP Shimla 9 vide letter no 1246-51 dt. 01/07/2017 Letter sent to The commissioner Excise & Taxation vide letter no 1763-66 vide letter no 02/08/2017 |  | Approved of drawings awaited. |  |
| 25 | 4941 | C/O type-IV qtrs. On the roof of office building of DPRO Nahan. |  |  |  |  | Roof plan from EE, Nahan Div. vide letter no 6183-84 dt. 15/10/14. |  |  |  |  |  |  | Sketch drgs Issued to EE, Nahan Div. Vide letter no 5375-78 dt. 27/01/15. |  | Work of Type-II Qtrs 2 Nos completed and handed over. Work of type-IV qtr. 1 No. is in progress. |  |
| 26 | 4864 | Welcome gate on NH-72 at Kala Amb, Poanta sahib on Dehradoon road. |  | Letter no. 656-58 dt. 06/014 Letter no 41 dt. 02/05/15 |  |  | Letter no 9874-77 dt. 06/01/2014 Letter no 2669-72 dt. 22/05/15. |  |  |  |  |  |  | Letter no 430-32 dt. 19/06/2014 Letter no 75-77 dt. 23/05/15. |  | Its pertain to NH |  |
| 27 | 4941 -do- | DPRO at Nahan (Addition of type –IV in 2nd floor) -do- |  |  |  |  | 6183-84 dated 15-10-14 (roof Plan of DPRO office received) |  |  |  |  |  |  | 3554-58 dated 1-12-14 5165-67 dated 15-1-15 5375-78 dated 27-1-2015 Sketch drawings issued for approval |  | Work completed for type-IV qtr. on 2nd floor. |  |
| 28 | 7175 |  | Type I,II,III qtrs. For sub Tehsil Complex at Ronhat. |  |  |  |  |  |  |  |  |  |  | Layout plan Type I,II,III,Qtr. Supplied to EE, Shillai Div. Vide letter no 2671-72 dated 07/11/2016 |  | Complete upto plinth level & Column work is in progress of type-II qtr. |  |
| 29 | 7175 |  | Tehsil Office building at Poanta Sahib. | Letter no 96148 dt. 23/09/14 |  |  | Letter no 8159-60 dt. 09/01/13 |  |  |  |  |  |  | Revised Drawing/structure drawing sent to EE, Poanta Sahib division vide letter no 3709-10 dated 12/01/17 |  | 60% work completed |  |
| 30 | 7175 |  | C/O residential accommodation of naib tehsildar and others office staff at Rohnat distt. Sirmour. |  |  |  |  |  | Vide letter no 113340 dt. 26/08/2017 |  | Vide letter no 6384-86 dated 30/09/2016. |  |  | Standard working drawings for type-I,II&III qtrs. Issued to EE, Shillai Div. vide letter no 2543-45 dated 27/10/2016. |  | Complete up to plinth level & Column work is in progress of type-III qtr. |  |
| 31 | 8040 |  | Mini sectt. At Sangrah distt. Sirmour. | Received from Sudhir kumar Asstt. Commissioner vide letter no 92844 dt. 30/05/14. |  |  | Vide letter no 899-903 dt 13/05/2015. |  | Vide letter no 103138 dt. 17/07/15 |  | Received from SE Nahan vide letter no 4846-47 dt 13/01/16. |  |  | Working drgs. Issued to EE,Sangrah Division vide letter no 1648-49 dt. 10/08/16. |  | Frame structure complete & Finishing work & Roofing is in progress. |  |
| 32 | 8040 |  | C/o Mini Secretariat Building at Shillai Distt. Sirmour H.P. |  |  |  | From EE. Shillai Div. vide letter no, 2173-76 dated 31/05/2016 |  |  |  |  |  |  | Letter No. 944-47, dated: 15.06.2016 Letter send to D.C. Nahan Distt. Sirmour |  | Framed structure and masonry completed Plastering work 90% completed & finishing work is in progress. |  |
| 33 | 8157 |  | C/O Sub-tehsil office building and residence at Pajhhota(Nohri) Tehsil Rajgarh Distt Sirmour. |  |  |  | From EE. Rajgarh Div. vide letter no 2467-70 dated 31/05/2016 |  |  |  |  |  |  | Letter send to DC Sirmour at Nahan for approval vide letter no 790-93 dt. 06/06/16. |  | Site development and approach road completed and further work is in progress. |  |
| 34 | 8201 |  | Working Women hostel at paonta Sahib and nahan (Moginand) |  |  |  | Vide letter no 1808 dated 31/01/2017.. |  | Vide letter no 5984 dated 30/03/2017 |  | Vide letter no 868-69 dated 16/05/2017 |  |  | Working drawing a/w specification sent to EE, Nahan Division vide letter no 2730-32 dt. 07/10/17 |  | Estimate for working women hostel at Moginand has been submitted to the Director Women & Child development Shimla vide S.E. 12th Office letter No. 362-63 dated 21-07-2017 for amounting to Rs. 336. 00 Lacs for arraigning the A/A & E/S which is still Awaited |  |
| 35 | 8211 |  | C/O sub treasury building at Dadahu. |  |  |  | Vide letter no 91-93 dated 24/04/2017 |  |  |  |  |  |  | The special secretary(fin)-cum-Director Treasuries, accounts& lotteries HP. Requested for detailed requirements vide letter no 1117-21 dt. 22/06/2017 |  | Requirement of building is still awaited. |  |
| 36 | 8215 |  | Contour site plan of Sub-tehsil building at narag Tehsil pachhad distt. Sirmour HP. |  |  |  | Videl letter no 4199-4202 dated 03/07/2017 |  |  |  |  |  |  | Layout plan and working drgs. sent to EE, Rajgarh division vide letter no 2216-18 dt. 04/09/2017 |  | Detailed estimate under preparation |  |
| 37 | 6341 |  | C/O Type- IV residence for district Treasury officer nahan. |  |  |  |  |  |  |  |  |  |  | Demanded from EE, Nahan division Contour site plan & the vacant land be farwarded vide letter no 1102-05 dt. 21/06/2017 |  | Work awarded to the Contractor. |  |

Note :- Red portion shows  deposit works Which are not counted in Total Projects