15TH CIRCLE UNA (MISC.)

| Sr. NO. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Status of Projects Supplied by SE. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 7963 | C/O Office-cum-Residence of Commandant Home Guards 12th Battalian Una |  |  | Letter No. 292 on dated 15-01-2016 | Letter No. 16981-82 dated 21-11-2015 | Working Drawings issued alongwith specification s vide Letter No. 205-08 dated 19-04-2016 | Geotechnical investigation is being carried out and structural design is in progress. |
| 2 | 7135 | .C/O 4 NO. Quarters at Police Post at Pandoga Tehsil Haroli Distt Una |  | letter No. 15893-94 dated 05-11-15 |  | Letter No. 1091-92 dated 3/4/2016 | Layout & working drawings issued. Letter NO. 106-08 dated 07-04-16 | Work is in progress. |
| 3 | 7135 | C/O Multipurpose hall for Indian Reserve Batallian Complex at Bangarh Distt. Una ii) IRB Bangarh |  | From S.E vide letter No. 385-88 dated 13/4/2017 |  |  | Letter No. 2921-22 dt. 30/10/2017 regarding the optimum thickness of the Brick walls required for the purpose keeping in view the ht. of the structure | .Work is in progress. Site inspected by Sr. Architect 25/1/2018 and letter regarding the thickness of brick walls submitted vide letter No. – Revised working drawings are awaited. |
| 4 | 7135 | C/O State Vigilance and anti corruption bureau building (Modern New Police Station at Una) and staff quarters. |  | 276-77 dated 7/4/2014 |  |  | Working Drawings issued 3379-81 dated 22/11/2014 | Detailed estimate has been prepared as amount of Rs. 50lac was made available by the concerned department on dated 7/9/2017 and further process is being carried out. |
| 5 | 8045 | C/O Taxi stand over bus stand at Amb. |  | 10946-47 dt.25/2/14 |  |  | Sketch drawing issued for feasibility & approval.3878-80 dt 18/1/14 | NO correspondence has been received from the concerned department. |
| 6 | 8016 | Combined office building at Bangana | Revised requirement vide letter No. 5165-66 dated 19/8/17 | 15289-92 dt. 29-01-16 |  | Letter no. 1452-53 dated 1/5/2016 | Layout plan & working Drawings issued vide letter No. 201-04 dt. 19/4/2016 | Received requirement of SDM /Election office Tehsidar office & welfare office sent to Chief Architect Shimla vide EE Bangana letter No. 5165-66 dt. 19/8/2017 for evolving working drawings. |
| 7 | 8083 | C/O Office accommodation for Zila Sainik Welfare at Unn. | Letter No. 1646 dated 06/10/16 | Letter No 9926-28 dated 12/9/2014 |  |  | Working drawings issued for feasibility & approval vide Letter No. 381-84 dated 06/05/2017 | The case has been forwarded to the concerned department for T&CP clearance vide letter No. 1069-72 dated 20/6/2017 and the same is still awaited. |
| 8 | 8047 | C/O Secondary standard laboratory & working standard laboratory at village Rampur teh. & distt. Una HP. | Letter No. 3639 dated 17/12/2016 |  |  |  | Working Drawings issued for approval Letter No.4045-48 dated 07/02/17 | Feasibility has been submitted vide EE Una letter No. 1796-97 dt. 9/5/2017 and preparation of estimate is in progress. |

LIST OF WORK, 15TH  CIRCLE UNA – REST HOUSE

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 9 | 6045 | C/o Rest House at Amb. (Additional Accommodation VIP suites as per CM announcement |  | Letter No. 5597-98 dt. 26/8/2016 |  |  | As per Cm Announcement on dated 14/4 2016 the drawings were prepared and issued to EE vide Letter No. 4002-04 dated 4/02/2017 | Estimate sent to CE (HZ) Hamirpur & approval awaited. |
| 10 | 6045 | C/o additional V.I.P. suite in existing PWD., Rest House at Bangana | 5075-76, dated: 16/10/2014 |  |  |  | Drawing issued 3484-55, dated: 26/11/2014 | The estimate submitted to the Pr. Secy. (PWD) to the Govt. of HP had received back vide letter NO PBW (B&R) B(5) (1) /2003 dt. 7/9/2019 with the remarks that there is no Justification for addition & alteration in PWD rest house at Bangana. |
| 11 | 7823 | C/o residential colony of Revenue department at Haroli and SDPO Office cum residence at Haroli | 324, dated: 4/2/2015 | 18667-69, dated: 19/2/2015 |  | 2983-85 dated 21-05-15 | Layout plan &drawing issued vide letter 36-40, dated: 6/4/2015 | SDPO office Cum residence work is in progress. |
| 12 | 7823 | C/o Mini Sectt. at Una | 3046, dated: 21/12/2010 | 10809-11, dated: 8/9/2010 & 15624-25, dated: 01/12/2010 | 1130-31, dated: 24/11/2011 | 21594-95, dated: 19/03/2011 | Working drawing issued vide letter No. 5986-90, dated: 29/03/2012 | Working estimate has been prepared. Existing structures is to be dismantled after permission from the concerned department. |
| 13 | 7823 -do- | i)Residential Colony of Revenue Department at Haroli Una ii)(SH: C/O SDPO office cum residence at Haroli) |  | 18667-69 dt. 19/02/2015 | 324 dated 04/02/2015 | 2983-85 dated 21/05/2015 | Letter issued to EE Una for revised contour site plan vide letter No. 1387-89 dt. 29/06/2015 | SDPO office Cum residence work is in progress. |
| 14 | 7823 | Combined office Building at Amb | 30/09/2016 | 8361-63 dated 26/10/2016 |  |  | Letter issued by worthy CA to E.E Bharwain for rectifying the requirements as per instructions of Special Secretary. vide Letter No.3016-18 dt. 25/11/2016 | .Consolidation requirement still awaited from SDM. |
| 15 | 8016 | C/O Mini Sectt. Bangana Una | Dated 11.09-2012 vide letter no.6461 -63 | letter No. 9702-03dated 8-10-15. letter No.15289-92 dated 29-01-16 |  |  | Layout plan alongwith Working drawings issued For feasibility & approval letter No. 201-04 dated 19-04-2016 | Work does not appear in budget book. |
| 16 | 7823 | C/O Sub Treasury Office building at Amb distt. Una |  | Letter no. 7778-79 dated 23/9/2017 |  |  | Letter issued tto Special Secretary cum Director regarding detailed requirements. Vide letter No. 2897 -98 dated 27/10/2017 | Revised contour plan and photographs are yet to be submitted. |

Note :- Red portion shows  deposit works Which are not counted in Total Projects